## Slide 1: 500 final-years registered in 7 days
Free workshop: “Build Your First AI Project in 60 Minutes”
Who
Final-year B.Tech/BE students (CSE, IT, ECE, AI/DS) in placement season, mostly tier-2/3 colleges.
Insight (hypothesis)
Their resume says “AI” but shows no shipped project. Generic webinars get ignored because the outcome is vague.
Promise
Leave in 60 minutes with a working AI project you can show recruiters. Free, live, hands-on.
Budget ₹2,000 · 7 days · all projections are hypotheses to validate, not results
Notes: SLIDE 1: TARGET AUDIENCE & VALUE PROPOSITION
Key Talking Points:
1. Target Persona: Final-year B.Tech/BE students (CSE, IT, ECE, AI/DS) facing campus placements, particularly across tier-2 and tier-3 colleges.
2. The Core Bottleneck: Students have AI coursework on their resumes, but zero deployed projects that impress technical interviewers.
3. The High-Converting Promise: Not a generic webinar or passive lecture. In exactly 60 minutes, students build, test, and deploy a real working AI project to put directly on their GitHub and resume.
4. Growth Mindset: Everything presented here is a hypothesis designed for rapid validation within the first 48 hours.

## Slide 2: Three channels, one message: “Ship an AI project before your next interview”
A. Campus WhatsApp groups
10 student connectors forward a ready-made message and poster into placement and department groups. Peer trust beats a brand post. Metric: registrations per connector (goal 15+).
B. Clubs and communities
Coding clubs, GDSC-style chapters, Discord and LinkedIn groups get a short pitch plus a 30-second demo clip. Metric: sign-ups per community.
C. Referral loop
Each registrant gets a personal link. Top 3 referrers win prizes. Metric: share rate (goal 25%) and sign-ups per sharer.
Paid is not a main channel: ₹800 sits in reserve and is only used if Day 4 is behind pace
Notes: SLIDE 2: THREE-CHANNEL DISTRIBUTION STRATEGY
Key Talking Points:
1. Channel A - WhatsApp Connectors (Target: 250 regs): Peer distribution beats brand posts. 10 campus connectors post vetted copy into placement groups. Connector incentive: ₹50 thank-you per connector once they reach 15+ registrations (performance-gated).
2. Channel B - Clubs & Communities (Target: 140 regs): Coding clubs and student chapters receive a customized 30-second live build teaser.
3. Channel C - Referral Viral Loop (Target: 117 regs): Registrants receive an immediate invite link on the confirmation screen to unlock an AI Placement Toolkit. 25% share rate × 1.2 sign-ups = K-factor of 0.30.
4. Capital Efficiency: ₹800 (40% of total budget) is held strictly in reserve as a conditional paid test only if Day 4 pacing lags.

## Slide 3: Seven days and ₹2,000
Day | Action | Cumulative goal
1 | Build kit, recruit 10 connectors | 40
2 | Wave 1: connectors post in groups | 120
3 | Wave 2: clubs and communities | 210
4 | Checkpoint; fallback if under 270 | 300
5 | Referral prize push, proof post | 390
6 | “Closes tomorrow” urgency | 450
7 | Last call and reminders | 500
Budget | ₹
Connector thank-you (10 × ₹50, paid at 15+ regs) | 500
Referral prizes (₹300 / ₹200 / ₹100) | 600
Paid test reserve (only if behind) | 800
Buffer for UPI fees | 100
Total | 2,000
Tools (Google Sheets, free Canva, free hosting) cost ₹0 · owners: me for content, connectors for distribution
Notes: SLIDE 3: 7-DAY MILESTONE SCHEDULE & ₹2,000 BUDGET
Key Talking Points:
1. Cumulative Milestone Curve: 40 (D1) -> 120 (D2) -> 210 (D3) -> 300 (D4) -> 390 (D5) -> 450 (D6) -> 500 (D7).
2. The Critical Day 4 Checkpoint: Day 4 target is 300 cumulative registrations. 90% pacing threshold is 270. If we are under 270 on Day 4, contingency triggers fire immediately.
3. Strict Budget Allocation: ₹500 for connectors, ₹600 for referral leaderboard prizes (₹300/₹200/₹100), ₹800 paid reserve, ₹100 payment buffer = ₹2,000 total.
4. Unit Economics: Effective CAC at 500 registrations is exactly ₹4.00 per student.

## Slide 4: The funnel adds up to 507 (hypotheses)
Channel | Reach | Conversion | Registrations
A. WhatsApp connectors | 5,000 | 5% | 250
B. Clubs and communities | 3,500 | 4% | 140
C. Referral loop | 390 first-wave × 25% share | 1.2 sign-ups each | 117
Total |  |  | 507
Behind at Day 4 (under 270)
Release the ₹800 paid test, add 5 connectors in colleges with zero sign-ups.
Behind at Day 6
Switch to deadline urgency and ask the top connectors for one more group push.
Ahead of pace
Hold the paid reserve and spend effort on the reminders instead.
Reach and conversion rates are my assumptions; I have no NxtWave audience data. Replace them after the first 48 hours
Notes: SLIDE 4: FUNNEL ARITHMETIC & CONTINGENCY ENGINE
Key Talking Points:
1. Funnel Mathematics:
- Direct Acquisition (Wave 1): WhatsApp (5,000 @ 5% = 250) + Clubs (3,500 @ 4% = 140) = 390 registrations.
- Referral Amplification (Wave 2): 390 × 25% share rate × 1.2 sign-ups = 117 registrations.
- Total Organic Base Case = 507 registrations (+7 buffer over 500 goal).
2. Pre-Committed Decision Triggers:
- Day 4 Behind (<270): Deploy ₹800 Meta/Instagram paid ad targeting final-year engineers in tier-2/3 colleges (est. 40-50 regs @ ₹16-20 CPL), onboard 5 replacement connectors in zero-registration colleges.
- Day 6 Behind: Switch all messaging to 24-hour urgency ("Workshop closes tonight"), direct connector outreach, and spot cash prizes.
- Ahead of Pace: Protect the ₹800 cash reserve and reinvest effort into live workshop attendance reminders.

## Slide 5: Working asset: Workshop Launchpad
Full-stack referral tracking, live student registration gateway, and automated pacing engine. Production-grade demonstrable application with end-to-end attribution.
Link Studio
Generates a unique code, tracked URL and ready WhatsApp message per connector, club or student.
Live Dashboard
Actual vs target by day, channel split, leaderboard and an automatic fallback alert under 90% of pace.
Funnel Model
Editable reach and conversion inputs that show whether the plan still reaches 500.
Success: 90%+ of registrations carry a code · pace gap visible daily · 25% share rate · about ₹4 per registration (₹2,000 ÷ 500)
Live Local Demo: http://localhost:3000/ | Standalone HTML: index.html (Zero-dependency Node server & REST API)
Notes: SLIDE 5: WORKSHOP LAUNCHPAD PRODUCT DEMONSTRATION
Key Talking Points:
1. Why Build a Tool? Growth engineers build systems, not just spreadsheets. Workshop Launchpad gives the campaign owner live visibility into pacing and attribution.
2. Link Studio: Generates unique collision-resistant codes, UTM campaign URLs, and multi-angle WhatsApp messaging templates.
3. Registration Demo Gateway: A real student registration experience that captures attribution, logs the lead, and provides the student their own viral invite link.
4. Live Dashboard: Real-time actual vs. target SVG pacing curve, daily ingestion breakdown, referral leaderboard, and automatic contingency trigger warnings.
5. Funnel Model: Live recalculation with K-factor viral multiplier and paid reserve toggle.
6. Architecture: Built with a lightweight zero-dependency Node.js REST API with file persistence, fully runnable standalone or client-server.